## Lev2(OSP Rev)
Recommend- |  | Year 1 2003/04 |  |  |  | Year 2 2004/05 |  |  |  | Year 3 2005/06 |  |  |  | Year 4 2006/07 |  |  |  | Year 5 2007/08
action |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Annual assessments of op support units | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q2
2 | Create 24/7 joint SCD/TP gateway | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q2
3 | Increase transparency of TP tasking | bar: Year 1 2003/04 Q3 to Year 1 2003/04 Q4
4 | Protocol req op support units to inform local BOCU about operations in their areas | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q1
5 | Include use of op support resources in BTCGs | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q1
6 | Raise community awareness re use of op support resources | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q1
7 | Measure activities and outcomes of op support units in most efficient way | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q3
8 | Retain officers past retiral/increase People Bank | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q2
9 | Assess benefits of further civilianisation | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q2
10 | Second trainee detectives to SCD | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q2
11 | Directly recruit experienced investigators | bar: Year 1 2003/04 Q3 to Year 2 2004/05 Q2
12 | Increased analysis of Level 2 crime | bar: Year 1 2003/04 Q3 to Year 1 2003/04 Q4
13 | Evaluate impact on BOCU of Level 2 drugs init | bar: Year 1 2003/04 Q3 to Year 3 2005/06 Q1
COSTS
FINANCIAL |  | Year 1 2003/04 Q1: Year 1 2003/04; Year 2 2004/05 Q1: Year 2 2004/05; Year 3 2005/06 Q1: Year 3 2005/06; Year 4 2006/07 Q1: Year 4 2006/07; Year 5 2007/08 Q1: Year 5 2007/08 | Cumulative total
COST |  | Year 1 2003/04 Q2: FYTD (B); Year 1 2003/04 Q4: FYTD (A); Year 2 2004/05 Q2: FYTD (B); Year 2 2004/05 Q4: FYTD (A); Year 3 2005/06 Q2: FYTD (B); Year 3 2005/06 Q4: FYTD (A); Year 4 2006/07 Q2: FYTD (B); Year 4 2006/07 Q4: FYTD (A); Year 5 2007/08 Q2: FYTD (B); Year 5 2007/08 Q4: FYTD (A) | CTTD (B) | CTTD (A) | Variance
| Rec1 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0 | 0 | 0 | 0
| Rec2 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 700000; Year 3 2005/06 Q1: 1400000; Year 4 2006/07 Q1: 1400000; Year 5 2007/08 Q1: 1400000 | 4900000 | 0 | -4900000
| Rec3 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec4 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec5 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec6 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec7 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec 8 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec 9 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec 10 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec 11 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec 12 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| Rec 13 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 3 2005/06 Q1: 0 | 0 | 0 | 0
| TOTAL COSTS | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 700000; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 1400000; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 1400000; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 1400000; Year 5 2007/08 Q3: 0 | 4900000 | 0 | -4900000
OPPORTUNITY |  | Year 1 2003/04 Q1: Year 1 2003/04; Year 2 2004/05 Q1: Year 2 2004/05; Year 3 2005/06 Q1: Year 3 2005/06; Year 4 2006/07 Q1: Year 4 2006/07; Year 5 2007/08 Q1: Year 5 2007/08 | Cumulative total
COST |  | Year 1 2003/04 Q2: FYTD (B); Year 1 2003/04 Q4: FYTD (A); Year 2 2004/05 Q2: FYTD (B); Year 2 2004/05 Q4: FYTD (A); Year 3 2005/06 Q2: FYTD (B); Year 3 2005/06 Q4: FYTD (A); Year 4 2006/07 Q2: FYTD (B); Year 4 2006/07 Q4: FYTD (A); Year 5 2007/08 Q2: FYTD (B); Year 5 2007/08 Q4: FYTD (A) | CTTD (B) | CTTD (A) | Variance
| Rec1 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec2 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec3 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec4 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec5 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec6 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec7 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 13500; Year 3 2005/06 Q1: 0; Year 4 2006/07 Q1: 0; Year 5 2007/08 Q1: 0 | 13500 | 0 | -13500
| Rec8 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec9 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec10 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec11 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec12 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec13 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| TOTAL COSTS | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 13500; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 13500 | 0 | -13500
TOTAL COSTS OF CARRYING OUT REVIEW
BENEFITS | bar: Year 1 2003/04 Q1
Cashable savings |  | Year 1 2003/04 Q1: Year 1 2003/04; Year 2 2004/05 Q1: Year 2 2004/05; Year 3 2005/06 Q1: Year 3 2005/06; Year 4 2006/07 Q1: Year 4 2006/07; Year 5 2007/08 Q1: Year 5 2007/08 | Cumulative total
|  | Year 1 2003/04 Q2: FYTD (B); Year 1 2003/04 Q4: FYTD (A); Year 2 2004/05 Q2: FYTD (B); Year 2 2004/05 Q4: FYTD (A); Year 3 2005/06 Q2: FYTD (B); Year 3 2005/06 Q4: FYTD (A); Year 4 2006/07 Q2: FYTD (B); Year 4 2006/07 Q4: FYTD (A); Year 5 2007/08 Q2: FYTD (B); Year 5 2007/08 Q4: FYTD (A) | CTTD (B) | CTTD (A) | Variance
| Rec1 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec2 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec3 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec4 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec5 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec6 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec7 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec 8 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 107000; Year 3 2005/06 Q1: 214000; Year 4 2006/07 Q1: 214000; Year 5 2007/08 Q1: 214000 | 749000 | 0 | -749000
| Rec 9 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec 10 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec 11 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 69750; Year 3 2005/06 Q1: 139500; Year 4 2006/07 Q1: 139500; Year 5 2007/08 Q1: 139500 | 488250 | 0 | -488250
| Rec 12 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
| Rec 13 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0 | 0 | 0 | 0
TOTAL CASHABLE SAVINGS |  | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 176750; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 353500; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 353500; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 353500; Year 5 2007/08 Q3: 0 | 1237250 | 0 | -1237250
NET CASHABLE SAVING - Variance to date | bar: Year 1 2003/04 Q1 to Year 1 2003/04 Q2
Non-cashable |  | Year 1 2003/04 Q1: Year 1 2002/03; Year 2 2004/05 Q1: Year 2 2003/04; Year 3 2005/06 Q1: Year 3 2004/05; Year 4 2006/07 Q1: Year 4 2005/06; Year 5 2007/08 Q1: Year 5 2005/06 | Cumulative total
(efficiency) savings |  | Year 1 2003/04 Q2: FYTD (B); Year 1 2003/04 Q4: FYTD (A); Year 2 2004/05 Q2: FYTD (B); Year 2 2004/05 Q4: FYTD (A); Year 3 2005/06 Q2: FYTD (B); Year 3 2005/06 Q4: FYTD (A); Year 4 2006/07 Q2: FYTD (B); Year 4 2006/07 Q4: FYTD (A); Year 5 2007/08 Q2: FYTD (B); Year 5 2007/08 Q4: FYTD (A) | CTTD (B) | CTTD (A) | Variance
| Rec1 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec2 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec3 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec4 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec5 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec6 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec 7 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec 8 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec 9 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec 10 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec 11 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec 12 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
| Rec 13 | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 |  | 0
TOTAL NON-CASHABLE SAVINGS |  | Year 1 2003/04 Q1: 0; Year 1 2003/04 Q3: 0; Year 2 2004/05 Q1: 0; Year 2 2004/05 Q3: 0; Year 3 2005/06 Q1: 0; Year 3 2005/06 Q3: 0; Year 4 2006/07 Q1: 0; Year 4 2006/07 Q3: 0; Year 5 2007/08 Q1: 0; Year 5 2007/08 Q3: 0 | 0 | 0 | 0
NET NON-CASHABLE SAVING - Variance to date | bar: Year 1 2003/04 Q1 to Year 1 2003/04 Q2
Key non financial benefits |  | Year 2 2004/05 Q1: Baseline performance; Year 3 2005/06 Q1: Current Performance; Year 4 2006/07 Q1: Target/milestone; Year 5 2007/08 Q1: Trend commentary
Ensuring that Operational Support units are focused on MPS priorities as defined by NIM. |  | Year 2 2004/05 Q1: Information not yet available; Year 3 2005/06 Q1: Information not yet available
Retention of experienced officers on BOCUs. |  | Year 2 2004/05 Q1: Information not yet available; Year 3 2005/06 Q1: Information not yet available
Improved MPS response to Level 2 crime. |  | Year 2 2004/05 Q1: Information not yet available; Year 3 2005/06 Q1: Information not yet available

## Glossary
COSTS
Financial cost | Actual direct increase in budget required to implement recommendation/review, e.g. actual increase of staff needed to perform a function, or increase in police overtime.
Opportunity cost | The income or benefit foregone as a result of carrying out a particular deicison, when resources are limited or when mutually exclusive projects are involved, e.g. is staff time is required to implement recommendations/reviews then this time can not be spent on other MPS work.
Capital cost | Expenditure on the acquisition, creation or enhancement of fixed assets, with a cost in excess of £5,000 and a life of more than a year.
Revenue cost | Expenditure to meet the continuing cost of services including wages and salaries and purchase of materials.
BENEFITS
Cashable saving | Direct saving in budget achieved through the redeployment of financial resources or a reduction in the total resource requirement.
Non-cashable saving | Saving achieved through an improvement in performance, but where financial resources are not released, i.e. those which are not immediately cashable but which lead to increased output, or avoid the need for additional expenditure in the longer term.
Net cashable saving | Total Cashable Saving - Total Financial Cost
Net non-cashable saving | Total Non-Cashable Saving - Total Opportunity Cost
Non-Financial Benefit | Benefit derived from performance improvement that does not directly relate to a financial or efficiency saving.
FYTD (B) | Financial Year to Date (Budgeted)
FYTD (A) | Financial Year to Date (Actual)
CTTD (B) | Cumulative Total to Date (Budgeted)
CTTD (A) | Cumulative Total to Date (Actual)